## WBS
Activity |  | Tasks |  | # of units | Unit price($) | Estimated Cost
1 | Plan |  |  | 34 |  | 480
| 1.1 |  | Create stakeholders engagment plan | 5 | 20 | 100
| 1.2 |  | Create stakeholders communication plan | 5 | 20 | 100
| 1.3 |  | Create team charter | 20 | 10 | 200
| 1.4 |  | Create WBS | 2 | 20 | 40
| 1.5 |  | Risk Management | 2 | 20 | 40
2 | Design |  |  | 80 |  | 5200
| 2.1 |  | Create software Architecture | 40 | 50 | 2000
| 2.2 |  | Review software Architecture | 24 | 100 | 2400
| 2.3 |  | Rework software Architecture | 16 | 50 | 800
3 | Implement |  |  | 2400 |  | 36000
| 3.1 |  | Develop Mobile APP | 1600 | 15 | 24000
| 3.2 |  | Develop the website | 400 | 15 | 6000
| 3.3 |  | Develop application to be used by customer | 400 | 15 | 6000
4 | Test |  |  | 960 |  | 13440
| 4.1 |  | Test Mobile app | 640 | 14 | 8960
| 4.2 |  | Test the website | 160 | 14 | 2240
| 4.3 |  | Test application to be used by customer | 160 | 14 | 2240
5 | Deploy |  |  | 1064 |  | 16080
| 5.1 |  | Take approval from customer | 24 | 20 | 480
| 5.2 |  | Deploy with small number of shops | 200 | 15 | 3000
| 5.3 |  | rework based on feedback | 40 | 15 | 600
| 5.4 |  | full deployment | 800 | 15 | 12000
6 | Closure |  |  | 48 |  | 960
| 6.1 |  | Document list of open issues | 16 | 20 | 320
| 6.2 |  | Document list of lesson learned | 16 | 20 | 320
| 6.3 |  | team appraisal | 16 | 20 | 320
| Sum |  |  | 9172 |  | 144320
Estimation assumptions
|  | 1 | Hr Team hire the project team according to the communicated schedule
|  | 2 | Customer submits the full requirments on 15-apr-2023
|  | 3 | Supplier delivers the required tools on 28-aug-2023