## Sheet1
Description of Risk | Impact Description | Probability | Impact | Risk Rating | mitigation strategy | Risk plan | Risk owner | status
Software engineer had left and we can't hire replacment | Impact in our sale and technical progress | Moderate | High | High | Transfer | 1- Assign to another team in the company
2- double the effort to find SW engineer
supplier doesn't deliver on time | delay in delivering items to customers | very likely | extreme | High | mitigate | liability clause in contract
Someone of the team gets infected by covid-19 | Impact on business activities | very likely | moderate | High | mitigate | 14 days of isolation for the infected
Apply on the vaccine once it's available