## WBS
1 | Plan |  | 2 | Design |  | 3 | Implement
| 1.1 | Create stakeholders engagment plan |  | 2.1 | Create software Architecture |  | 3.1 | Develop Mobile APP
| 1.2 | Create stakeholders communication plan |  | 2.2 | Review software Architecture |  | 3.2 | Develop the website
| 1.3 | Create team charter |  | 2.3 | Rework software Architecture |  | 3.3 | Develop application to be used by customer
| 1.4 | Create WBS
| 1.5 | Risk Management
4 | Test |  | 5 | Deploy |  | 6 | Closure
| 4.1 | Test Mobile app |  | 5.1 | Take approval from customer |  | 6.1 | Document list of open issues
| 4.2 | Test the website |  | 5.2 | Deploy with small number of shops |  | 6.2 | Document list of lesson learned
| 4.3 | Test application to be used by customer |  | 5.3 | rework based on feedback |  | 6.3 | team appraisal
|  |  |  | 5.4 | full deployment